## Read me
eMudhra response workbook
Version 0.1.0 · 26 October 2026 · Proposed — no decisions have been taken and no team data has been entered. Companion to ACTION_PLAN.md, RISK_TIERS.md, COMPLETION_TRACKER.md and playbooks/ in the eMudhraResponse repository.
Purpose | Capture the decisions the response needs, and track every service, platform, long-tail item, exception and hunt to closure using the pack's six mandatory fields and closure routes A/B/C.
Where to keep it | Keep the populated copy in the internal incident or change system. Do not commit populated inventories, hostnames or logs to a public repository (Completion tracker rule).
Who fills what | Incident lead: Decisions, Facts. Service and platform owners: Service tracker, Platform assurance. Desktop/mobile: Browser & desktop. Owners and supplier management: Long tail. PKI: Availability. Risk owners: Exceptions. SOC: Hunt log.
Sheets
Dashboard | Calculated summary: counts by priority and status, headline KPIs. Do not edit.
Decisions | Decision register D-01 to D-16, with options and a recommendation. Record the decision, rationale and date in the yellow columns.
Service tracker | One row per service or managed asset group. Columns map to the pack's six mandatory fields. Priority is calculated from Impact × Susceptibility.
Platform assurance | One row per standard configuration (Route A records) with emSign, AAA and No-CT test results and deployment coverage.
Browser & desktop | One row per managed browser/OS configuration; calculates whether the browser and desktop proviso is met.
Long tail | Non-browser, vendor-controlled and supplier items found by egress telemetry and inventories.
Availability | Certificates we present, and partner endpoints we call, that chain to affected emSign roots.
Exceptions | Risk exceptions with compensating controls, approver and expiry.
Hunt log | Retrospective hunts H1–H6 from PB-14, with the retention gap back to 30 April 2025.
Facts | Dated incident facts with confidence and source; recheck daily while the incident is open.
Playbooks | Index of PB-00 to PB-16 with owner team and link.
Lists | Dropdown values, the priority matrix and two assumptions (proviso threshold, hunt window start).
Legend
White cell | Enter data. Dropdowns appear where a column has fixed values.
Yellow cell | Key input or decision field — the cells management is asked to complete.
Grey cell | Calculated by formula. Do not overwrite.
Grey italic row | Worked example showing the expected format. IDs start with EX- and are excluded from the Dashboard. Overwrite or delete.
Navy header | Input column.
Slate header | Calculated column.
Priority
Priority = Impact (H/M/L, as defined in RISK_TIERS.md §2) × Verifier susceptibility (A–D or Unknown). See Lists!T1 for the matrix and key. Defined in RISK_TIERS.md §4; approval is decision D-01. Indicative windows (decision D-03, not approved): P1 contain 72 h / close 7 days; P2 14 days; P3 30 days; P4 normal cycle.

## Dashboard
eMudhra response — dashboard
Calculated from the other sheets; rows whose ID starts with EX- (examples) are excluded. Do not edit.
Headline indicators
P1 records not closed | 0
Records with susceptibility Unknown | 0
Records overdue | 0
Records with availability flag = Y and not closed | 0
Total records (excluding examples) | 0
Browser/desktop configurations meeting the proviso | 0 of 10
Long-tail items with vendor status Pending or No response | 0
Availability items not done | 0
Exceptions approved and expiring within 14 days | 0
Decisions still open | 16
Hunts done (of H1–H6) | 0 of 6
Service tracker: records by priority and status
Priority | Assessing | Exposed | Remediating | Closed A | Closed B | Closed C | Exception / blocked | Total
P1 (incl. to assess) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P2 (incl. to assess) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P3 (incl. to assess) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
P4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Records with no priority yet (impact or susceptibility blank) are not counted above.

## Decisions
ID | Decision required | Why now | Options | Recommendation | Decision owner | Forum / approver | Needed by | Status | Decision taken | Rationale | Date decided | Review date | Linked items
D-01 | Adopt a prioritisation model for the response | Tier 2 currently mixes vendor-protected browsers with exposed API clients | 1) Keep the version 1 four tiers 2) Impact × verifier susceptibility matrix, keeping tier labels for impact 3) Separate lists per platform team | Option 2, as defined in RISK_TIERS.md. Version 1 tiers map to impact | Incident lead | Response steering | 2026-10-28 | Open |  |  |  |  | RISK_TIERS §2–4; Lists!T1
D-02 | Accept vendor protection as closure for browsers and desktop OS stores | Vendors protected browsers 17–20 Oct; enterprise conditions can defeat it | 1) Treat as fixed without evidence 2) Accept with the four-condition proviso and a coverage report 3) Require per-device testing | Option 2, with the coverage threshold in Lists!U16 (proposed 95%) | Head of EUC | Response steering | 2026-10-28 | Open |  |  |  |  | ACTION_PLAN §5; PB-01; Browser & desktop sheet
D-03 | Set indicative target windows per priority | Version 1 set no target windows, so overdue work couldn't be distinguished from on-track | 1) No windows; agree per service 2) Indicative P1 72 h contain / 7 days close, P2 14 days, P3 30 days, P4 normal cycle 3) Stricter fixed SLAs | Option 2, as indicative targets; overdue items reported, not penalised | CISO | Risk committee | 2026-10-28 | Open |  |  |  |  | RISK_TIERS §4; ACTION_PLAN §10
D-04 | Replace our certificates that chain to emSign ECC Root CA - G3 | Chrome removes the root on Tue 27 Oct; legitimate sites under it will fail | 1) Replace external certificates immediately; internal within 14 days 2) Wait for eMudhra migration support 3) Accept Chrome failures for low-traffic sites | Option 1. PKI owns; no extension for customer- or partner-facing endpoints | Head of PKI | Incident lead | 2026-10-27 | Open |  |  |  |  | PB-13; Availability sheet
D-05 | Accept availability impact of removing emSign roots from our managed trust stores | Root removal (NSS, Ubuntu, certifi, webpki-roots) breaks partners still using those roots | 1) Remove the root and handle breakages by time-boxed exception 2) Delay removal until partners migrate 3) Distrust intermediates only where the platform supports it | Option 1, plus option 3 where supported (Windows, Java blocklists). Never restore trust globally | Incident lead | Response steering | 2026-10-29 | Open |  |  |  |  | PB-03; PB-05; PB-13
D-06 | Handle the Sectigo AAA cross-sign route on Windows and Java | AAA still matters on Windows, Java and older/vendor bundles | 1) Distrust the specific intermediates and cross-certificates 2) Remove AAA Certificate Services root 3) Rely on Sectigo revocation only | Option 1; remove AAA only where the vendor prescribes it (e.g. Oracle) and after a positive-control test | Head of PKI | Incident lead | 2026-10-29 | Open |  |  |  |  | PB-02; PB-04
D-07 | TLS-inspection proxy policy for untrusted or revoked upstream certificates | For inspected traffic the proxy, not the browser, decides trust | 1) Block 2) Warn and allow 3) Re-sign with an untrusted CA | Option 1 (block), with an exception path for business-critical partners | Network security lead | Incident lead | 2026-10-28 | Open |  |  |  |  | PB-09
D-08 | Scope of the retrospective hunt | Keys were weak from 30 Apr 2025; any chain to them is presumptively forged | 1) No historical hunt 2) Hunts H1–H6 over available retention, gap recorded 3) Restore archived logs to cover the full window | Option 2 now; option 3 only for P1 data sources if option 2 finds anything | SOC lead | Incident lead | 2026-10-30 | Open |  |  |  |  | PB-14; PB-12; Hunt log
D-09 | Long-tail cut-off date and exception policy | The tail won't close on one date; without a cut-off, items drift | 1) No cut-off 2) Cut-off date; after it, unremediated items need an exception with an approved compensating control 3) Hard deadline with shutdown | Option 2; cut-off 25 Nov 2026 | CISO | Risk committee | 2026-11-02 | Open |  |  |  |  | ACTION_PLAN §6; PB-11; Exceptions
D-10 | Supplier assurance approach | Suppliers that process our data validate certificates on their side | 1) Rely on public statements 2) Formal request to critical suppliers only 3) Formal request to all suppliers | Option 2 (payments, identity, SaaS with regulated data, managed security providers) | Supplier risk lead | Response steering | 2026-11-02 | Open |  |  |  |  | PB-11 template; Long tail
D-11 | Regulatory and notification stance | Obligations differ by jurisdiction and regulator | 1) No position 2) No notification for exposure alone; Legal defines triggers on evidence of exploitation 3) Precautionary notification | Option 2; Legal confirms regulators per jurisdiction | General Counsel | Risk committee | 2026-10-30 | Open |  |  |  |  | PB-14 triage step 4
D-12 | Reporting unit and cadence | Mixed units double-count shared platforms | 1) Count deployments 2) Count services; executive update twice weekly until P1 closed 3) Daily executive updates | Option 2; daily only for P1 open items, blockers and outages | Incident lead | Response steering | 2026-10-28 | Open |  |  |  |  | Dashboard
D-13 | Internal test service for systems without test-site egress | Many P1 servers can't reach the external test hosts | 1) Offline chain bundle only 2) Internal test service run by PKI 3) Temporary egress exceptions | Option 1 by default; option 2 if more than a handful of P1 systems can't be tested | Head of PKI | Incident lead | 2026-10-30 | Open |  |  |  |  | PB-00
D-14 | Criteria for closing the incident | Without criteria the incident never formally closes | 1) Close when browsers are fixed 2) Close when P1/P2 are closed or excepted, proviso met, hunts complete and availability track closed 3) Close when everything is closed | Option 2; remaining P3/P4 move to business-as-usual vulnerability management | CISO | Risk committee | 2026-11-02 | Open |  |  |  |  | ACTION_PLAN §2
D-15 | In-house mobile apps | Bundled trust anchors aren't fixed by OS updates | 1) No action 2) Review every app handling credentials or payments; minimum-version enforcement if affected 3) Review all apps | Option 2 | Head of mobile | Response steering | 2026-11-02 | Open |  |  |  |  | PB-10
D-16 | Staff communications | Avoid alarm and bypass behaviour; prepare for 27 Oct site failures | 1) All-staff notice 2) Service desk knowledge article only 3) No communication | Option 2; all-staff notice only if exploitation is found | Head of comms | Incident lead | 2026-10-27 | Open |  |  |  |  | PB-15
Note on F1: Proposed owner role — map to a named person.
Note on J1: Record the decision as taken, in one or two sentences.

## Service tracker
Record ID | 1. Service / asset group | 1. Accountable owner | Team | Environment | 2. Impact (H/M/L) | 2. Verifier susceptibility | Priority | Version 1 tier (1–4) | 2. Rationale | 3. Trust configuration | 3. Assurance ref or custom detail | Playbook | 4. Closure route | 4. Status | 4. Remedy or reason no change | 5. Evidence link | 6. Outstanding work | 6. Target date | Discovered / assigned | Availability flag | Code-signing relevant | Days open | Overdue
EX-1 | Payments API (outbound to card processor) | J. Smith (example) | Payments | Production | H | C | P1 | 1 | Sends card-holder data to an external API from a Java service with its own cacerts | Custom trust | Java app-cacerts copy | PB-04 | B | Remediating | Removed verified emSign/AAA anchors from managed store copy; JVM restart scheduled | CHG-0000 (example) | Restart remaining 2 nodes — J. Smith | 2026-10-30 | 2026-10-26 | N | N | 0
EX-2 | Standard Windows 11 managed desktops | EUC lead (example) | EUC | Production | M | A | P4 | 2 | Browsers and Windows store protected by vendor push; proviso checks pending | Standard platform | PA-EX-1 | PB-01 | A | Assessing — exposure unknown | No change expected; confirm proviso |  | Coverage report — EUC lead | 2026-10-30 | 2026-10-26 | N | N | 0
Note on B1: Field 1: application/service or managed asset group, and covered environment.
Note on F1: H = Tier 1 impact; M = Tier 2/3; L = Tier 4 or low consequence.
Note on G1: A–D or Unknown. See Lists!T8 for the key.
Note on H1: Calculated from Impact × Susceptibility (Lists!T1).
Note on I1: Optional: the version 1 tier, for records created before 26 Oct.
Note on J1: Trust role and business impact in a sentence.
Note on L1: Route A record ID (e.g. PA-...) or a brief description of custom trust.
Note on Q1: Existing change/test/config record or shared assurance link.
Note on R1: Issue and owner, or 'None' if closed.
Note on U1: Y if the service presents or depends on certificates under affected emSign roots (PB-13).

## Platform assurance
Assurance ID | Standard configuration | Owner team | Verifier / stack | Vendor remedy applied | Remedy version / date | emSign route | AAA route | No-CT test | Positive control | Instances covered | Instances in scope | Coverage % | Known exclusions | Evidence link | Status | Review date
PA-EX-1 | Ubuntu 24.04 LTS server build | Linux platform | OpenSSL / system bundle | ca-certificates 20260816ubuntu0.24.04.1 | 20 Oct 2026 | Pass | N/A | Pass | Pass | 412 | 430 | 95.81% | 18 hosts pending maintenance window | CHG-0000 (example) | In progress | 2026-11-09
Note on H1: Required where AAA is still trusted: Windows, Java, older or vendor bundles. N/A for current Mozilla-derived bundles.

## Browser & desktop
Managed configuration | Vendor mechanism | Vendor date (2026) | Owner | 1. Egress to vendor updates OK | 1. No policy blocks updates | 2. Supported versions | 3. Not decrypted, or proxy validated | 4. Images / offline refreshed | Representative test | Devices in scope | Devices confirmed | Coverage % | Proviso met | Notes / exclusions
Windows 11 + Chrome | CRLSet block (17 Oct); Chrome Root Store removal of emSign ECC Root CA - G3 (27 Oct) | 17 Oct / 27 Oct | [10 empty] | No
Windows 11 + Edge | Microsoft block | 20 Oct | [10 empty] | No
Windows + Firefox ESR | OneCRL via Remote Settings | 17 Oct | [10 empty] | No
macOS + Safari | Apple block | 19 Oct | [10 empty] | No
macOS + Chrome | CRLSet; Chrome Root Store change | 17 Oct / 27 Oct | [10 empty] | No
VDI image (name) | Per browser above; image refresh required | [11 empty] | No
ChromeOS | CRLSet; Chrome Root Store change | 17 Oct / 27 Oct | [10 empty] | No
Android with Google Play services | Equivalent block via Google Play services | c. 19 Oct | [10 empty] | No
Android without Google Play services | Not covered by Play services delivery — OEM update needed | [11 empty] | No | Treat as long tail (PB-11) until the OEM confirms a fix.
iOS / iPadOS | Apple block | 19 Oct | [10 empty] | No
Proviso: covers the browser and OS trust store only. Not covered: macOS /usr/bin/curl and other CLI tools, Java, Python, Node and Go apps, Electron apps, VPN/ZTNA and management agents, developer toolchains — record those on the Long tail sheet. Vendor dates are from press reports of vendor statements; confirm on the Facts sheet. Coverage threshold is Lists!U16 (assumption pending D-02).
Note on E1: Condition 1: devices can reach vendor update services.
Note on F1: Condition 1: no policy disables component updates, Remote Settings or Windows root/disallowed auto-update.
Note on G1: Condition 2: supported browser/OS; Android Play services current.
Note on H1: Condition 3: traffic not TLS-inspected, or the inspection proxy passed PB-09.
Note on I1: Condition 4: VDI, kiosk, golden images, long-offline devices. N/A if none.

## Long tail
ID | System / product | Category | Discovered via | Owner | Vendor / supplier | Impact | Susceptibility | Priority | Vendor status | Vendor ref / date | Interim control | Exception ID | Target date | Status | Notes
EX-LT-1 | Building management system cloud connector | OT / IoT / facilities | Egress telemetry | Facilities IT (example) | Vendor X (example) | M | D | P2 | Pending | Ticket 0000, 24 Oct | Egress restricted to vendor endpoints | EXC-EX-1 | 2026-11-20 | In progress | Vendor ETA mid-November

## Availability
ID | Endpoint / hostname | Direction | Scope | Owner | Issuer | Root | Affected by | Replacement CA / action | Planned date | Status | Notes
EX-AV-1 | partner-api.example.net | We call | External | Integration owner (example) | emSign ECC CA - G3 (example) | emSign ECC Root CA - G3 | Both | Partner to replace certificate | 2026-11-06 | In progress | Time-boxed exception EXC-EX-2 if it breaks first

## Exceptions
Exception ID | Linked record | Reason | Compensating control | Residual risk | Requested by | Approver | Approved date | Expiry / review date | Status | Days to expiry
EXC-EX-1 | EX-LT-1 | Vendor fix not available until mid-November | Egress restricted to two vendor endpoints; alert on any other destination | M | Facilities IT (example) | CISO delegate (example) | 2026-10-27 | 2026-11-20 | Approved | 25
Formulas:
Days to expiry = IF(OR([Expiry / review date]="",[Status]="Closed",[Status]="Rejected"),"",[Expiry / review date]-TODAY())

## Hunt log
Hunt | Description | Data source | Retention starts | Searched from | Searched to | Gap to window start (days) | Query reference | Hits | Disposition | Analyst | Date | Status
H1 | Binaries signed under the two affected code-signing intermediates | EDR file-signature telemetry | [9 empty] | Open
H2 | Upstream certificates issued by the six TLS intermediates | TLS-inspection / SWG logs | [9 empty] | Open
H3 | Same issuers in passive TLS (TLS 1.2 and older only) | NDR / Zeek x509.log | [9 empty] | Open
H4 | Peer certificate details on P1 integrations | Application TLS logs | [9 empty] | Open
H5 | Certificates for our domains chaining to the intermediates | Certificate Transparency | [9 empty] | Open
H6 | Unexpected JWKS kid values or SAML signing-certificate changes | IdP and API logs | [9 empty] | Open
Note on G1: Days between the hunt window start (Lists!U18, 30 Apr 2025) and the earliest date searched.

## Facts
Date (2026) | Event | Confidence | Source | Last checked | Owner
30 Apr 2025 | Eight intermediate keys generated with P-384 private values below 256; recoverable from public data | Secondary | Free Press Journal; BleepingComputer (citing Mozilla) | 2026-10-26 | Response lead
— | Six TLS intermediates, two code-signing (reported as trusted by Microsoft); eMudhra says none issued end-entity certificates | Secondary | CSO Online; Free Press Journal | 2026-10-26 | Response lead
17 Oct | Report received; Chrome CRLSet and Firefox OneCRL block (no browser update or restart needed) | Primary (Google) | blog.google; The Hacker News | 2026-10-26 | Response lead
19 Oct | Apple block; Sectigo revokes eight AAA cross-certificates; Android protection via Google Play services | Secondary | BleepingComputer; Technobezz; Sectigo advisory | 2026-10-26 | Response lead
19 Oct | Go 1.27.3 and 1.26.10 published (reject chains with the eight keys; rebuild required) | Verified (release); Secondary (content) | proxy.golang.org toolchain index; Rescana | 2026-10-26 | Response lead
19 Oct | Rust webpki-roots 1.0.10 removes emSign ECC Root CA - G3 | Verified | crates.io package contents | 2026-10-26 | Response lead
18–23 Oct | Python certifi 2026.10.18+ removes emSign ECC Root CA - G3; 2026.10.23 keeps only emSign Root CA - G1 | Verified | PyPI package contents | 2026-10-26 | Response lead
20 Oct | Microsoft block | Secondary | Free Press Journal | 2026-10-26 | Response lead
20 Oct | Ubuntu 24.04 ca-certificates 20260816ubuntu0.24.04.1 blocklists emSign ECC Root CA - G3 (LP #2171507) | Verified | Package changelog | 2026-10-26 | Response lead
20–21 Oct | Node.js, Bun, Debian, FreeBSD fixes pending; macOS /usr/bin/curl still accepted chain after Apple block | Secondary | Rescana; lilting.ch; CSO Online | 2026-10-26 | Response lead
26 Oct | Node.js 22.22.0 built-in roots still include emSign ECC Root CA - G3 | Verified | tls.rootCertificates check | 2026-10-26 | Response lead
21 Oct | No confirmed malicious use; one key published on GitHub; no TLS certs under the six intermediates in CT before block | Secondary | BleepingComputer; iTnews | 2026-10-26 | Response lead
23 Oct | Oracle JDK advisory updated: action needed even on listed builds | Vendor advisory | ops.java/emudhra | 2026-10-26 | Response lead
27 Oct | Chrome removes emSign ECC Root CA - G3 from Chrome Root Store (~30,000 certificates to migrate, eMudhra estimate) | Primary (Google); Secondary (estimate) | blog.google | 2026-10-26 | Response lead

## Playbooks
Code | Title | Owner team | Typical priority | File (relative to this workbook)
PB-00 | Test and evidence | Security/PKI (all teams read) | — | playbooks/PB-00-test-and-evidence.md
PB-01 | Browsers and desktop operating systems | Desktop / EUC | P3–P4 under proviso | playbooks/PB-01-browsers-and-desktop-os.md
PB-02 | Windows servers, .NET and PowerShell | Windows platform; app owners | P1–P3 | playbooks/PB-02-windows-and-dotnet.md
PB-03 | Linux, Unix and macOS command-line tools | Linux/Unix platform | P1–P3 | playbooks/PB-03-linux-and-unix-hosts.md
PB-04 | Java applications and Java-based products | App owners; platform | P1–P2 | playbooks/PB-04-java.md
PB-05 | Python applications, jobs and tools | App owners | P1–P2 | playbooks/PB-05-python.md
PB-06 | Node.js, Bun and Electron apps | App owners; desktop; vendors | P1–P2 | playbooks/PB-06-nodejs-and-electron.md
PB-07 | Go, Rust, PHP, Ruby and other runtimes | App owners | P1–P2 | playbooks/PB-07-go-rust-php-ruby.md
PB-08 | Containers, Kubernetes, serverless and CI/CD | Container platform / DevSecOps | P1 for pipelines | playbooks/PB-08-containers-kubernetes-and-cicd.md
PB-09 | Proxies, gateways, load balancers and TLS inspection | Network / security engineering | P1 for inspection proxies | playbooks/PB-09-proxies-gateways-and-tls-inspection.md
PB-10 | Mobile devices and in-house mobile apps | Mobile / MDM; app teams | P1–P4 | playbooks/PB-10-mobile.md
PB-11 | Vendor products, appliances, agents and suppliers | System owners; supplier management | By impact | playbooks/PB-11-vendor-products-appliances-and-suppliers.md
PB-12 | Code signing, application control and software distribution | Endpoint security; software distribution | P1 | playbooks/PB-12-code-signing-and-application-control.md
PB-13 | Our certificates, partner endpoints and availability | PKI / certificate management | Time-critical | playbooks/PB-13-our-certificates-and-availability.md
PB-14 | SOC: retrospective hunt and monitoring | SOC / incident response | P1 | playbooks/PB-14-soc-threat-hunt.md
PB-15 | Service desk knowledge article | Service desk | From 27 Oct | playbooks/PB-15-service-desk.md
PB-16 | Identity integrations and mutual TLS | IAM / API platform | P1 | playbooks/PB-16-identity-and-mtls.md

## Lists
Impact | Susceptibility | Status | Route | Trust configuration | Yes/No | Yes/No/NA | Test result | Vendor status | Long-tail category | Discovered via | Decision status | Playbook | Generic status | Exception status | Availability direction | Scope | Availability cause | Priority matrix (impact × susceptibility)
H | A | Assessing — exposure unknown | A | Standard platform | Y | Y | Pass | Fixed | Server outbound client | Egress telemetry | Open | PB-00 | Open | Requested | We present | External | Chrome 27 Oct root removal | Impact \ Susceptibility | A | B | C | D | Unknown
M | B | Exposed — action required | B | Custom trust | N | N | Fail | Pending | Runtime bundle | CMDB | Decided | PB-01 | In progress | Approved | We call | Internal | Trust-store root removal | H | P3 | P1 | P1 | P1 | P1 (assess)
L | C | Remediating | C | Unknown |  | N/A | Inconclusive | Not affected | Container / serverless | Software inventory | Deferred | PB-02 | Done | Rejected |  |  | Both | M | P4 | P2 | P2 | P2 | P2 (assess)
| D | Closed — A: covered by platform assurance | Not yet chosen |  |  |  | Not tested | No response | CI/CD / supply chain | Container registry | Superseded | PB-03 | Blocked | Expired |  |  |  | L | P4 | P3 | P3 | P3 | P3 (assess)
| Unknown | Closed — B: application-specific validation |  |  |  |  | N/A | No fix planned | Desktop non-browser software | Supplier register |  | PB-04 |  | Closed
|  | Closed — C: not applicable to assessed role | [6 empty] | Network / security appliance | TLS inspection logs |  | PB-05
|  | Exception / blocked — owner and review date required | [6 empty] | VPN / ZTNA / agent | Hunt |  | PB-06 | [5 empty] | Susceptibility key
[9 empty] | OT / IoT / facilities | Owner report |  | PB-07 | [5 empty] | A | Vendor-pushed block or CT enforced (browsers; OS store already updated)
[9 empty] | In-house mobile app |  |  | PB-08 | [5 empty] | B | Uses the OS store; update available but not yet confirmed
[9 empty] | Supplier / SaaS |  |  | PB-09 | [5 empty] | C | Own bundle or compiled roots (certifi, Node, Java cacerts, Go, Rust, container images)
[9 empty] | Inbound mTLS |  |  | PB-10 | [5 empty] | D | Embedded / appliance / vendor-controlled; no fix yet
[12 empty] | PB-11 | [5 empty] | Unknown | Not yet assessed — schedule assessment at the shown priority
PB-12
PB-13
[12 empty] | PB-14 | [5 empty] | Proviso coverage threshold | 95% | Assumption pending decision D-02: share of in-scope devices that must be confirmed before a configuration counts as Validated.
PB-15
[12 empty] | PB-16 | [5 empty] | Hunt window start (key generation) | 2025-04-30 | Source: Mozilla incident report as cited by press, 20–21 Oct 2026 (see Facts sheet).